## Sheet1
BUG LIST OF "BLOOD CELL"
Bug ID | Bug Description | Steps to Reproduce | Severity | Type of Bug | Screenshot | Developer Status | Tester Status
Bug 01 | Shading is appearing in Instruction Box (GLOBAL ISSUE) | 1. Open the Simulation 2. Start playing the simulation 3. See the Instruction box with the green outlined | Minor | UI | Screenshot 01 | solved, in moto it workes fine | Closed
Bug 02 | Text is appearing Missing | 1. Open the Simulation 2. Tap on Functions of Blood Cells 3. Opt Correct answer from the bullets 4. LOAD button appear | Minor | Texture | Screenshot 02 | solved | Closed
Bug 03 | Two instruction box overlapping (Let me know) | 1. Open the Simulation 2. Level 1 >> Start playing the simulation 3. While playing u reach to step II of level 1 where we have to collect all type of blood cell | Minor | UI, Texture | Screenshot 03 | solved | Closed
Bug 04 | Immunity Level box is not disappearing | 1. Open the Simulation 2. Tap on Functions of Blood Cells 3. Opt Correct answer from the bullets for LYMPHOCYTES 4. Fill the immunity to a level it becomes green | Major | UI | Screenshot 04 | solved | Closed
Bug 05 | Bulltes Button is not displaying Overlap with immunity box | 1. Open the Simulation 2. Tap on Functions of Blood Cells 3. Opt Correct answer from the bullets for LYMPHOCYTES 4. Complete the level, Moving forward | Major | UI, Functionality | Screenshot 05 | solved | Closed
Bug 06 | No Space between two instruction box | 1. Open the Simulation 2. Level 1 >> Start playing the simulation 3. Description about the cell display when user click on label | Minor | UI | Screenshot 06 | solved | Closed
Bug 07 | QUERY : Drop down arrow | 1. Open the Simulation 2. Level 1 >> Start playing the simulation 3. Select the cell >> its name display, just next to it arrow is there | Minor | Functionality | NO | solved | Closed
Bug 08 | Level 1 button is appearing next to level 2 button, when level 1 is already completed | 1. Open the Simulation 2. Level 1 >> Start playing the simulation 3. Complete the Level 1 and come to next screen | Minor | UI | Screenshot 07 | solved | Closed
Bug 09 | Sound missing | 1. Open the Simulation Level 2 2. Well Done & Try Again Sound is missing | Major | Functionality | no | solved | Closed
Bug 10 | Green Boundary line is missing of well done | 1. Open the Simulation 2. Start Playing Level 1 3. Outline missing from Well done box | Minor | UI | NO | ui Box issue | Closed
bug 11 | Simulation lagging | 1. Open the Simulation 2. Start Playing Level 1 keep playing it moving forward it lags | Minor | UI | NO | optimized | Closed
bug 12 | Score Outline is flickering | 1. Open the Simulation 2. Start Playing Level 2 3. Score on the top >> its outline is flickering | Minor | UI | NO | ui Box issue | Closed
NOTE : For the screenshot, check given path \\192.168.1.222\Artist Work Area2\QA\Biology\Blood Cell\QA Screenshots
NEW ISSUES
Bug 13 | No Pointer sound (Let me know) | 1. Open the simulation 2. Tap on Level 2 >> Click on bullet tab >> drag the pointer no sound is there | Minor | Sound | no | solved | Closed
Bug 14 | Text box is overlapping | 1. Open the simulation 2. Tap on Level 2 >> Click on bullet tab >> Score text box and bullet text box is overlapping | Major | UI | no | solved | Closed
Bug 15 | Color of Try Again | 1. Open the simulation 2. Tap on Level 2 >> Try Again Color | Minor | UI | no | solved | Closed
Bug 16 | Simulation not Opening from the begining, once it is completely done &restart again | 1. Open the simulation 2. Once complete the simulation and click on restart button it is not starting from the begining | Major | Functionality | Screenshot 08 | solved | Closed
Bug 17 | No Space between two instruction box | 1. Open the simulation 2. On completing level 1 >> OST appears that OST box is overlap with the button also the content is not appropriate | Major | UI | Screenshot 09 | solved | Closed
Bug 18 | No button sound | 1.Open the simulation 2. Tap on Level 2 >> Click on bullet button >> no sound | Minor | Sound | no | solved | Closed
Bug 19 | Add bullets instead of Star(*) | 1.Open the simulation 2. Click on Objective add bullets | Minor | UI | NO | solved | Closed
Bug 20 | Alignment of the score(let me know) | 1. Open the simulation 2. Alignment of Score (check ) | Minor | UI | NO | solved | Closed
Bug 21 | Score not moving | Level 2 >> Score not moving | Major | UI | NO | solved | Closed